## All Bug Reports
Test Case | Bug ID | Title/Summary | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reporter & Date | Assigned To | Environment | Attachments/References
TC_AUTH_002 | BUG-001 | User does not receive confirmation email after registration | - | 1.Hover on "My account" tab 2. Click on "Register" 3. Enter data 4.Click continue | user recives a confirmation email | No confirmation email is received after successful registration. | Major | High | New | Habeeba Sameh 12/4/2026 | Backend Developer | windows (chrome) | Links or filenames for screenshots, videos, or logs
TC_AUTH_003 | BUG-002 | System accepts invalid data in registration fields | System allow user to write numbers in the first and second name fields | 1.Hover on "My account" tab 2. Click on "Register" 3. Enter data 4.Click continue | Error message: "Please enter valid data type in name feild " | Account is created successfully, and a success message appears | Minor | Medium | New | Habeeba Sameh 12/4/2026 | Backend Developer | windows (chrome)
TC_AUTH_007 | BUG-003 | System does not enforce password complexity rules | System checks only length of the password and ignores complexity rules | 1.Hover on "My account" tab 2. Click on "Register" 3. Enter data 4.Click continue | Error message: " Password must be between 4 and 20 characters, including at least one uppercase letter, one number, and one special character" | System displays an error message: " Password must be between 4 and 20 characters!" and checks only the length of the password Does not enforce complexity rules | Critical | High | New | Habeeba Sameh 13/4/2026 | Backend Developer | windows (chrome)
TC_AUTH_012 | BUG-004 | System does not redirect the user to the login page after logging out |  | 1.Hover on "My account" tab 2. Click on "Logout" 3.Click on continue | The system redirect the user to the login page | The system redirect the user to the home page | Trivial | Low | New | Habeeba Sameh 12/4/2026 | Backend Developer | windows (chrome)
TC_AUTH_013 | BUG-005 | System allows user to return to an authenticated page after logout. | System allows user to use the browser back button to return to an authenticated page after logout | 1.Hover on "My account" tab 2. Click on "Logout" 3.Click on continue 4.Click on the browser back button 2 times | The user should be redirected to the login page or home page | System allowed the user to return to an authenticated page after logout. | Critical | High | New | Habeeba Sameh 12/4/2026 | Backend Developer | windows (chrome)
TC_AUTH_015 | BUG-006 TC_LOGIN_004 | User does not receive password reset email | System did not send password reset email to the user after entering a valid email address in the "Forgotten Password" page | 1.Hover on "My account" tab 2.Click on "Log in" 4.Click on "Forgotten Password" 5.Enter email address 6.Click continue | The system will display a successful message and send a password reset link to the email if it is valid. | the User did not recive password reset email | Major | High | New | Habeeba Sameh 12/4/2026 | Backend Developer | windows (chrome)
TC_AUTH_016 | BUG-007 TC_LOGIN_003 | Incorrect error message displayed for empty fields during login | System displayes "Warning: Your account has exceeded allowed number of login attempts. Please try again in 1 hour." when the user login with empty email field even it is the first try | 1.Hover on "My account" tab 2. Click on "Log in" 3.Enter password 4.Click login | Error message: "Email address or password field can't be empty " | Error message:"Warning: Your account has exceeded allowed number of login attempts. Please try again in 1 hour" | Minor | Medium | New | Habeeba Sameh 13/4/2026 | Backend Developer | windows (chrome)
TC_AUTH_018 | BUG-008 TC_SESSION_001 | System does not lock account after defined number of failed login attempts | System displayes an error message but the user still can login | 1.Hover on "My account" tab 2. Click on "Log in" 3. Enter wrong data 4.Click login (repeat) | Error message:"Warning: Your account has exceeded allowed number of login attempts. Please try again in 1 hour". And the system lock the account. | the system display an error message but the account is not locked | Critical | High | New | Habeeba Sameh 13/4/2026 | Backend Developer | windows (chrome)
TC_AUTH_024 | BUG-009 TC_SESSION_003 | Session token is not regenerated after logout and re-login | - | 1. Open Login page 2. Open DevTools > Application > Cookies 3. Enter valid data and click Login 4. Note the session token value 5. Logout 6. Login again with same data 7. Compare the new session token to the previous one | A new unique session token is generated for each login, the two tokens must be diffrent | The system is reusing the same session token across different login sessions | Critical | High | New | Habeeba Sameh 13/4/2026 | Backend Developer | windows (chrome)
TC_AUTH_026 | BUG-010 | Session cookie is missing HttpOnly, Secure, and SameSite flags | - | 1. Login with valid data 2. Open DevTools > Application > Cookies 3. Locate the session cookie 4. Check the HttpOnly and Secure flags | The session cookie has both HttpOnly = true and Secure = true flags enabled | HttpOnly, Secure, and SameSite all missing from Set-Cookie | Critical | High | New | Habeeba Sameh 13/4/2026 | Backend Developer | windows (chrome)
TC_NAV_007 | BUG_NAV_001 | Mega menu click redirects to About Us page instead of displaying categories | When user clicks on Mega Menu, the system redirects to About Us page instead of displaying categories list. This creates inconsistent behavior between hover and click actions | 1.Open website homepage 2.Hover over Mega Menu 3.Observe categories displayed 4.Click Mega Menu | Categories list should be displayed when clicking Mega Menu | User redirected to About Us page instead of categories list | Medium | High | Open | zahraa elabd – 14Apr 2026 | Dev Team | Chrome / Firefox / Edge – Windows 10
TC_NAV_012 | BUG_NAV_002 | Incorrect products displayed when selecting category | When selecting a category from navigation menu, products displayed do not match the selected category. | 1.Open homepage 2.Click any category (example: Apple) 3.Observe displayed products | Selected category should display relevant products | Different products from another category are displayed | High | High | Open | zahraa elabd – 14Apr 2026 | Dev Team | Chrome / Firefox / Edge – Windows 10
TC_NAV_015 | BUG_NAV_003 | Search results display incorrect product details | Search results show products that do not match the entered search keyword | 1.Enter product name in search bar 2.Click search 3.Observe displayed products | Products related to search keyword should be displayed | Different products displayed not matching search keyword | High | High | Open | zahraa elabd– 14Apr 2026 | Dev Team | Chrome / Firefox / Edge – Windows 10
TC_001 | BUG-001 | Product naming not related to filter/search | Product names displayed on the listing page are not matching or related to the applied filter criteria, causing incorrect product display. | 1- Log in 2- Select category from Mega menu 3- Observe the product names displayed | Product naming is correct and related to the filter | Naming is not related to filter (ex: Product Code: Product 3, 6, etc.) | Major | Medium | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_002 | BUG-002 | Product images not related to actual product | Product images shown on the listing/detail pages are mismatched and do not correspond to the correct product. | 1- Log in 2- Select category from Mega menu 3- Observe the product images | Image is related to the product | Images are not related to the product (ex: Product Code: Product 5, 7, 9, 11, etc.) | Major | Medium | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_005 | BUG-003 | Add to Cart shortcut triggers Quick View instead of adding to cart | The 'Add to Cart' shortcut button on the product listing page is incorrectly behaving as a Quick View trigger for certain products instead of adding the item to the cart. | 1- Log in 2- Select category from Mega menu 3- Stand on a product 4- Press cart icon (shortcut) 5- Observe the product on the cart page | Add the product to cart | It's acting as Quick View in some products (ex: product 3, 15) | Major | High | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_009 | BUG-004 | Product brand name displays incorrect brand | The brand name displayed on the product page does not match the actual brand the product belongs to, causing misinformation to the customer. | 1- Log in 2- Select category from Mega menu 3- Click on some product 4- See the product name and the brand | The product should be from this brand | The product is from a different brand than the displayed one (ex: product 6) | Major | Medium | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_013 | BUG-005 | Brand image not visible on product page | The brand image/logo on the product detail page is not rendering or displaying properly, appearing as a broken image or blank space. | 1- Log in 2- Select category from Mega menu 3- Stand on a product 4- Press compare icon 5- Observe compare page appears | The photo should be visible and related to the brand | The photo is not visible (ex: product 4) | Minor | Low | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_014 | BUG-006 | Redundant/duplicate products displayed in listing | The same product appears multiple times (as clones) on the product listing page, leading to duplicate entries and confusion for the user. | 1- Log in 2- Select category from Mega menu 3- Visualize products | The product appears once | There are multiple clones of the same product displayed | Major | Medium | New | saifallah/ 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_016 | BUG-007 | Product video shows 'Video Unavailable' error | Embedded product videos on the product detail page fail to load and display a 'Video Unavailable' error instead of playing the product video. | 1- Log in 2- Select category from Mega menu 3- Click on a product 4- Click on video icon | The video should run successfully | Displays 'Video Unavailable' (ex: product 14) | Minor | Low | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux 64
TC_017 | BUG-008 | Size selection options not displayed for in-stock products | Certain in-stock products do not show any available size options in the size selection dropdown/attribute section, preventing customers from selecting a size and completing the purchase. | 1- Log in 2- Select category from Mega menu 3- Click on some product 4- Click on available size | Display the available sizes | Some products in stock don't display any size available (ex: product 3, 15) | Critical | High | New | saifallah/ 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_018 | BUG-009 | No validation error for quantity below minimum | When a user enters a quantity value below the defined minimum threshold, the system does not display an error message and incorrectly accepts the invalid quantity. | 1- Log in 2- Select category from Mega menu 3- Click on some product 4- Enter a quantity below the minimum 5- Determine the quantity | Display an error message 'Invalid quantity' | It doesn't show an error message and accepts the Quantity | Critical | High | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_020 | BUG-010 | No validation error when entering 0 as quantity | The system allows a quantity of zero to be entered and accepted without showing any validation error, which should be an invalid input. | 1- Log in 2- Select category from Mega menu 3- Click on some product 4- Enter 0 in the quantity field 5- Determine the quantity | Display an error message 'Invalid quantity' | It doesn't show an error message and accepts 0 as the Quantity | Critical | High | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_021 | BUG-011 | No validation error for negative quantity input | Entering a negative number in the quantity field does not trigger any validation error, and the negative quantity is accepted by the system. | 1- Log in 2- Select category from Mega menu 3- Click on some product 4- Enter a negative number in the quantity field 5- Determine the quantity | Display an error message 'Invalid quantity' | It doesn't show an error message and accepts the negative Quantity | Critical | High | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_023 | BUG-012 | No error when entering quantity exceeding available stock | When a user enters a quantity greater than the available stock (e.g., 99999999), the system fails to display a validation error and accepts the out-of-range quantity. | 1- Log in 2- Select category from Mega menu 3- Click on some product 4- Enter quantity > stock (ex: 99999999) 5- Determine the quantity | Display an error message 'Invalid quantity' | It doesn't show an error message and accepts the Quantity | Major | Medium | New | saifallah/ 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_025 | BUG-013 | Out-of-stock product can be added to cart from Compare section | Products marked as out-of-stock are incorrectly allowed to be added to the cart from the Compare section without any error message being shown to the user. | 1- Log in 2- Select category from Mega menu 3- Click on some product 4- Click on compare 5- Click add to cart (for out-of-stock product) | Display an error message 'Out of stock' | It adds the product to the cart and doesn't display an error message | Critical | High | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_031 | BUG-014 | Review tab count does not update after adding a review | The review count shown on the Review tab does not increment after new reviews are successfully submitted, remaining at zero regardless of how many reviews are added. | 1- Log in 2- Select category from Mega menu 3- Click on some product 4- Scroll down to review 5- Submit a review | Count should increase every time a review is added | It remains zero | Minor | Low | New | saifallah / 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_004 | BUG-015 | In-stock products appear unavailable in the cart | Some products that are marked as 'in stock' incorrectly appear as unavailable when added to the cart, causing a mismatch between the product availability status displayed on the listing page and the actual cart state. | 1- Log in 2- Select category from Mega menu 3- Click on a product 4- Observe the availability 5- Add the product to cart 6- Observe the availability | Either (in stock) or (out of stock) and appear in the cart with the same state | Some in-stock products appear unavailable in the cart | Critical | High | New | saifallah/ 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC-4.2.4 | B-001 | Description When a user selects a specific category from the search bar dropdown (e.g. 'Laptops') and submits a search, the category selection is completely ignored. The system returns all products matching the keyword across every category instead of restricting results to the selected one. | all products on the main inventory page display the same placeholder image instead of their unique product images | 1. Navigate to https://ecommerce-playground.lambdatest.io 2. Click the search bar 3. Type 'Apple' as the search keyword 4. Open the category dropdown next to the search bar 5. Select 'Laptops' from the dropdown 6. Press Enter or click the search icon 7. Observe the results page | Only Apple products belonging to the Laptops category should be displayed. Products from Phones, Cameras, and other categories should be excluded. | All Apple products from every category were returned — MacBooks, iPhones, iPads, iMacs, and accessories all appeared regardless of the 'Laptops' category selection. The filter had zero effect on the result set. | Major | High | Open | Lama - Apr 18, 2026 | Development Team | Windows 10, Chrome Version 122.0.x
TC-4.2.5 | B- 002 | Search in subcategories' checkbox does not expand search results | The 'Search in subcategories' checkbox on the search results page has no functional effect. Enabling it does not increase or change the result set in any way. Results remain identical whether the checkbox is checked or unchecked, making the feature non-functional. | 1. Navigate to https://ecommerce-playground.lambdatest.io 2. Search for 'Apple' 3. On the search results page, note the total result count 4. Locate the 'Search in subcategories' checkbox 5. Check the checkbox 6. Re-submit the search 7. Note the new result count and compare 4-Check the cart icon badge (top right) | Enabling 'Search in subcategories' should expand the results to include products from child categories that are not returned by default. The result count should increase. | The result count and the returned products remained completely identical before and after enabling the checkbox. The feature appears to be non-functional — the checkbox state has no influence on the search query or results. | Minor | Medium | Open | Lama - Apr 18, 2026 | Development Team | Windows 10, Chrome Version 122.0.x
TC-4.3.1 | B-003 | Empty search submission returns all products instead of a validation message | When a user submits the search form with an empty input field, the system should either prevent submission and display a validation message or show a prompt to enter a keyword. Instead, it loads the search results page displaying all products in the store, which is misleading and functionally incorrect behaviour. | 1. Navigate to https://ecommerce-playground.lambdatest.io 2. Click the search bar 3. Leave the input completely empty 4. Press Enter or click the search icon 5. Observe the page that loads | The system should display a validation message such as 'Please enter a search term' and prevent the submission, or load a search page with a prompt to enter a keyword. No products should be displayed. | The search results page loaded and displayed all products in the store with no error message or validation prompt. The user receives no feedback that their input was empty, and the result appears as if all products match an empty query. | Major | high | Open | Lama - Apr 18, 2026 | Development Team | Android 16, Chrome Mobile
TC-4.3.3 | B-004 | Whitespace-only search input accepted and returns all products | Entering only whitespace (spaces) into the search bar and submitting produces the same incorrect behaviour as an empty search — all products are returned with no validation. The system is not trimming or validating whitespace input before processing the search query. | 1. Navigate to https://ecommerce-playground.lambdatest.io 2. Click the search bar 3. Type 5 or more space characters (no letters or numbers) 4. Press Enter or click the search icon 5. Observe the result | The system should recognise whitespace-only input as equivalent to an empty search and display a validation error or no-results message. No products should be returned. | The whitespace input was accepted without any validation. The search results page loaded and returned all products in the store — identical to the behaviour observed in BUG-003 (empty search). No validation message or error was displayed. | Minor | Medium | Open | Lama - Apr 18, 2026 | Development Team | Windows 10, Chrome Version 122.0.x
TC-4.5.2 | B-005 | Category filter from search bar dropdown completely ignored on results page | This is a duplicate root cause of BUG-001 observed specifically from the filter panel context. Selecting a category filter from the search bar dropdown before or during search has no effect on the displayed results. All products matching the keyword appear regardless of the category filter applied. | 1. Navigate to https://ecommerce-playground.lambdatest.io 2. Locate the search bar with the category dropdown 3. Select 'Cameras' from the category dropdown 4. Submit the search (leave keyword empty or use a broad term) 5. Observe the results page 6. Verify whether results are limited to Cameras category only | Only products belonging to the Cameras category should be shown. Products from Laptops, Phones, Tablets, and all other categories should be absent from results. | Products from all categories were returned. The Cameras category selection had no effect on the result set. The filter parameter appears to not be passed to or processed by the search logic. | Critical | High | Open | Lama - Apr 18, 2026 | Development Team | Windows 10, Chrome Version 122.0.x
TC-4.5.3 | B-006 | Result count does not update after applying a category filter | After applying a category filter on the search results page, the displayed result count (e.g. 'Showing 1-15 of 42') does not change. This is a direct consequence of the category filter having no effect (BUG-005), but also a separate UI issue — even if the filter were partially applied, the count indicator is not reflecting any state change. | 1. Navigate to https://ecommerce-playground.lambdatest.io 2. Perform a broad search (e.g. search for any common keyword) 3. Note the result count shown at the top of the results page 4. Apply a category filter from the dropdown 5. Observe the result count after the filter is applied | The result count should decrease (or change) to reflect only the products matching the applied category filter. | The result count remained completely unchanged before and after applying the category filter. The count indicator does not respond to filter application, giving the user no feedback that any filtering action occurred. | Major | Medium | Open | Lama - Apr 18, 2026 | Development Team | Windows 10, Chrome Version 122.0.x
TC-4.5.4 | B-007 | Removing a category filter shows no change due to filter never being applied | When a user applies a category filter and then removes it by resetting to 'All Categories', no visible change occurs in the result set. This is because the filter was never functionally applied in the first place (BUG-005). As a result, the filtered and unfiltered states are visually and functionally identical, making the filter removal action meaningless. | 1. Navigate to https://ecommerce-playground.lambdatest.io 2. Perform a search and note the result count 3. Apply a category filter (e.g. 'Cameras') 4. Note the result count — it will remain unchanged (BUG-006) 5. Reset the filter to 'All Categories' 6. Observe whether the result count or product list changes | Removing the filter should restore the full unfiltered result set. The count should return to the original number before any filter was applied. | No change occurred when removing the filter. The result set before filtering, during filtering, and after removing the filter were all identical. The filter system is entirely non-functional — applying and removing it produces no observable difference. | Major | Medium | Open | Lama - Apr 18, 2026 | Development Team | Windows 10, Chrome Version 122.0.x
TC-4.5.6 | B-008 | No empty state shown when filter returns zero matching products | When a user applies a category filter that logically conflicts with the search keyword (e.g. searching for 'Canon' and filtering by 'Tablets'), the system should display an empty state or a 'no products match' message. Instead, the filter is ignored and the original unfiltered results remain visible, giving the user false information about their search. | 1. Navigate to https://ecommerce-playground.lambdatest.io 2. Search for 'Canon' — results will show Camera products 3. Apply the category filter 'Tablets' 4. Observe whether results change or an empty state appears | Since no Canon products exist in the Tablets category, the results page should display an empty state message such as 'No products match your search and filter criteria.' | Canon camera products continued to display even after 'Tablets' was selected as the category filter. No empty state message appeared. The filter was silently ignored and the user received no indication that their filter-keyword combination had no valid matches. | Minor | Low | Open | Lama - Apr 18, 2026 | Development Team | Windows 10, Chrome Version 122.0.x
TC_CART_005 | BUG-001 | Out-of-Stock Product Can Be Added to Cart | The 'Add to Cart' button should be disabled or hidden for out-of-stock products. Instead, the product is added to the cart and only a warning message is shown inside the cart. | 1. Open LambdaTest website 2. Filter Out-of-Stock products 3. Hover on Sony VAIO 4. Click 'Add to Cart' | The 'Add to Cart' button is disabled or hidden for out-of-stock products, and no item is added to the cart. | The out-of-stock product was successfully added to the cart, displaying a warning message inside the cart instead of preventing the addition at the product page level. | High | High | Open | Mariam Waleed ¦17,apr.2026 |  | Web – LambdaTest ¦ Chrome 124 ¦ Win 11
TC_CART_008 | BUG-002 | Cart Total Rounding Error After Item Removal | After removing an item from the cart, the grand total displays a rounding error (e.g., $199.4 instead of $199.5), indicating incorrect rounding logic in the price calculation. | 1. Open LambdaTest website 2. Add Palm Treo Pro to cart 3. Note total price 4. Click Remove on the product 5. Observe updated total | Cart total recalculates automatically and reflects the correct updated subtotal based on remaining items with proper rounding. | Cart total displays incorrect value due to rounding error (e.g., 199.4 instead of 199.5). | Medium | Medium | Open | Mariam Waleed ¦17,apr.2026 |  | Web – LambdaTest ¦ Chrome 124 ¦ Win 11
TC_CART_011 | BUG-003 | Cart Icon Navigates to Summary Instead of Cart Page | Clicking the cart icon should navigate the user to the dedicated Cart page. Instead, it only displays a cart summary popup/dropdown without redirecting to the Cart page. | 1. Open LambdaTest website 2. Click on the Cart icon | Clicking the cart icon navigates to the cart page. | Clicking the cart icon displays a cart summary instead of navigating to the cart page. | Medium | Medium | Open | Mariam Waleed ¦17,apr.2026 |  | Web – LambdaTest ¦ Chrome 124 ¦ Win 11
TC_CART_014 | BUG-004 | Incorrect Grand Total Due to Wrong Line Item Price | The Cart page shows an incorrect line total for Palm Treo Pro ($2,703.90 instead of $2,703.92 for 8 × $337.99), causing Sub-Total, VAT, and Grand Total to all display wrong values. | 1. Open LambdaTest website 2. Add Palm Treo Pro (qty 8) and iPhone to cart 3. Open Cart page 4. Manually calculate total: 8 × $337.99 = $2,703.92 5. Compare with displayed value | Grand Total equals Sub-Total + Eco Tax + VAT calculated correctly. | Grand Total is incorrect — Palm Treo Pro line shows $2,703.90 instead of $2,703.92, causing Sub-Total, VAT, and Grand Total to all show wrong values. | Critical | High | Open | Mariam Waleed ¦17,apr.2026 |  | Web – LambdaTest ¦ Chrome 124 ¦ Win 11
TC_CART_017 | BUG-005 | Quantity +/– Controls Missing on Cart Page | The Cart page does not display the '+' and '–' quantity controls for cart items, preventing users from incrementally adjusting quantities directly from the cart. | 1. Open LambdaTest website 2. Add iPhone to cart 3. Click on Cart icon 4. Observe quantity controls for the item | Each cart item should have a '+' button to increase and a '–' button to decrease the quantity. | The '+' and '–' quantity controls are not present on the Cart page. | High | High | Open | Mariam Waleed ¦17,apr.2026 |  | Web – LambdaTest ¦ Chrome 124 ¦ Win 11
TC_CART_019 | BUG-006 | Invalid Quantity Input Removes All Cart Items Instead of Showing Error | Entering a letter, negative number, or special character in the quantity field should show a validation error. Instead, all items are silently removed from the cart. | 1. Open LambdaTest website 2. Add iPhone to cart 3. Click 'View Cart' 4. Click quantity input field 5. Clear value and type a letter (e.g., 'a'), negative number, or special character 6. Press Enter | An error message appears informing the user that only numeric values are allowed, and the quantity does not update. | All items are removed from the cart instead of showing a validation error message. | Critical | High | Open | Mariam Waleed ¦17,apr.2026 |  | Web – LambdaTest ¦ Chrome 124 ¦ Win 11
TC_CART_026 | BUG-007 | Cart Reverts to Previous State After Browser Back Navigation | After modifying the cart (removing items or changing quantities) and navigating back using the browser back button, the cart reverts to its previous state, losing all recent changes. | 1. Open LambdaTest website (logged in) 2. Add item to cart 3. Navigate to Cart page 4. Remove an item or change quantity 5. Click the browser back button 6. Navigate to Cart page again | Cart reflects the most recent changes; removed items stay removed and updated quantities persist. | After clicking browser back, the cart reverts to its previous state — removed items reappear and quantities reset to old values. | High | High | Open | Mariam Waleed ¦17,apr.2026 |  | Web – LambdaTest ¦ Chrome 124 ¦ Win 11
TC_CHECKOUT_009 | BUG-001 | User cannot place order when entering valid billing details on Checkout page | When the user enters valid billing and shipping details and clicks on "Confirm Order", nothing happens and the order is not placed. | 1. log in 2. click on desired product 3. Click add to cart 4. Open cart page | Product is shown as available in cart page | Product appear as soldout | Major | High | New | sara bassem/ 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_CHECKOUT_012 | BUG-002 | Incorrect total sum calculation in Checkout for authenticated users | During the execution of this test case , the system failed to accurately calculate the total price of products added to the cart. While the expected behavior is for the checkout page to display a mathematically correct sum of all items, the actual result showed an incorrect total, potentially leading to overcharging or undercharging the customer. | 1.Log in with credentials: testersix@test.com / wX@pxrw3Z5a2h2a. 2.Navigate to the product catalog and select a desired product. 3.Click Add to cart. 4.Open the Cart page. 5.Proceed to Checkout. 6.Observe the "Total Sum" and compare it against the individual item prices. | The sum is calculated correct | Sum is calculated wrong | Major | High | New | sara bassem/ 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_BILLING_014 | BUG-003 | Missing validation for phone number field in Guest Checkout | The system fails to validate the format of the phone number during the guest checkout process. When entering alphabetic characters ("abc") into the phone number field, the system allows the user to proceed and confirm the order instead of displaying the expected error message. This leads to invalid data being saved in the billing records. | 1.Access the website without logging in. 2.Add any product to the cart. 3.Navigate to the Cart page and click Checkout. 4.In the Billing/Guest Data section, enter "abc" in the Phone Number field. 5.Fill in the remaining required fields with valid data. 6.Click Continue and then Confirm Order. 7.Observe that the order is processed without any validation error. | An error message should be displayed indicating an invalid phone number format. | Guest proceeded to checkout successfully. | Medium | Medium | New | sara bassem/ 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_CHECKOUT_015 | BUG-004 | Lack of email format validation during Guest Checkout | The application fails to validate the email address format when an unregistered user (guest) completes an order. The system allowed an order to be successfully placed using a "non-real email" format (e.g., missing '@' or domain), rather than blocking the transaction with an appropriate error message. This prevents the system from sending order confirmations or digital receipts to the customer. | 1. Enter the website as a guest (do not log in). 2. Select a product and click Add to cart. 3. Navigate to the Cart page and click Checkout. 4. In the billing information section, enter a non-real email (e.g., testuser123 or user@com). 5.Complete the remaining required fields. 6.Click Continue and then Confirm Order. 7. Observe that the order is finalized and a success message is shown. | An error message should be displayed, and the "Confirm Order" action should be blocked until a valid email format is provided. | Order is placed successfully with an invalid email. | Major | High | New | sara bassem/ 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_ORDER_CONFIRM_022 | BUG-005 | Reward points not credited to account after successful order placement | When an authenticated user completes a purchase, the system fails to add the corresponding reward points to their account. Despite the order being confirmed, the "My Rewards" section remains empty or does not reflect the new points earned from the transaction. | 1. Log in with credentials: testersix@test.com / wX@pxrw3Z5a2h2a. 2. Add a product to the cart and proceed to Checkout. 3. Select "I want to use a new address" and fill in the required info. 4. Click Continue and then Confirm Order. 5. Navigate to My Account. 6. Click on My Rewards. 7. Observe that the reward points for the recent order are missing. | Reward points should be calculated and displayed in the "My Rewards" section after order confirmation. | Reward points are not displayed in the user's account. | Medium | Medium | New | sara bassem/ 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64
TC_ORDER_CONFIRM_023 | BUG-006 | Checkout form data is cleared upon page refresh | When a user is in the process of adding a new address during checkout, refreshing the page causes all entered information to be deleted. The system fails to persist the data in the form fields (session storage or local state), forcing the user to re-enter all details from scratch. | 1. Log in with credentials: testersix@test.com / wX@pxrw3Z5a2h2a. 2. Add a product to the cart and click Checkout. 3. Select "I want to use a new address". 4. Fill in the address form with the required information (Name, City, Address, etc.). 5. Refresh the browser page (F5 or Refresh icon). 6. Observe that all previously filled fields are now empty. | The entered information should be retained/persisted so the user doesn't lose their progress after a refresh. | The entered info gets deleted upon refreshing the page. | Medium | Medium | New | sara bassem/ 2025-04-17 | Dev Team | Web ¦ firefox ¦ linux64

## Summary (hidden)
Source File | Number of Bugs
SS2 | 15
H2 | 10
LL2 | 8
MM2 | 7
sarah2 | 6
ZZ2 | 3
Total | 49